## Sheet1
# | Feature | User Story | Story Point(s)
1 | Friend system – add golfers to a friend’s list | As a Player, I want to add golfers to a friend’s list so that I can contact other golfers easily. | 5
2 | Player profiles – handicap, favorite courses, play frequency, bio | As a Player, I want to create a player profile with my handicap, favorite courses, play frequency, and bio so that others can understand my playing level and preferences. | 5
3 | Edit profile information – update name, bio, preferences | As a Player, I want to edit my profile information so that my name, bio, and preferences stay accurate over time. | 2
4 | Nearby golfer discovery – find players within a customizable radius using GPS | As a Player, I want to discover nearby golfers within a customizable radius using GPS so that I can find players close enough to realistically meet up and play. | 5
5 | Nearby course discovery – find courses using proximity | As a Player, I want to discover nearby golf courses using proximity so that I can quickly find courses in my area. | 5
6 | In-app messaging – chat to coordinate rounds or meetups | As a Player, I want to message other golfers in the app so that I can coordinate tee times, logistics, and meetups. | 5
7 | Contact sync | As a Player, I want to sync my contacts so that I can quickly find friends who already use GolfR and connect with them. | 3
8 | Skill-based matching – based on handicap | As a Player, I want to match with golfers based on handicap so that I can play with people at a similar skill level. | 5
9 | Play style filters – casual / competitive / scramble / practice | As a Player, I want to filter matches by play style so that I can find golfers who want the same type of round (casual, competitive, scramble, or practice). | 3
10 | Availability matching – auto-pair players based on preferred time of play | As a Player, I want to match with golfers based on preferred times to play so that I can be paired with people whose schedules overlap with mine. | 3
11 | View own profile – see how profile appears in the app | As a Player, I want to view my own profile so that I can confirm how my information appears to other golfers. | 2
12 | Create private matches – host your own mini tournaments | As a Player, I want to create private matches so that I can host my own rounds or mini tournaments with selected golfers. | 8
13 | Live scorecards – track scores in real time with friends | As a Player, I want to use live scorecards so that I can track scores with friends during a round. | 13
14 | Automatic leaderboards – rankings for matches and tournaments | As a Player, I want automatic leaderboards so that I can see rankings and results for matches and tournaments without manually calculating. | 13
15 | Round history tracking – store past scores and stats | As a Player, I want round history tracking so that I can review my past scores and performance over time. | 8
16 | Performance insights – driving accuracy, GIR, putting | As a Player, I want performance insights like driving accuracy, GIR, and putting so that I can identify strengths, weaknesses, and trends in my game. | 13
17 | Handicap adjustment engine – calculate informal handicaps from past rounds | As a Player, I want an informal handicap adjustment engine so that my estimated handicap updates as I record more rounds. | 8
18 | Course reviews & ratings – pace, conditions, value | As a Player, I want to leave course reviews and ratings so that other golfers can judge pace, course conditions, and value before booking. | 3
19 | Seasonal challenges – monthly competitions (most rounds, lowest average) | As a Player, I want seasonal challenges so that I can stay motivated and compete in monthly goals like most rounds played or lowest average score. | 8
20 | Personal goals – set scoring or consistency targets | As a Player, I want to set personal goals so that I can track progress toward scoring and consistency targets. | 3
21 | Search bar – search for courses or usernames | As a Player, I want a search bar to search for courses or usernames so that I can find specific people or places quickly. | 5
22 | Logging in using email & password | As a Player, I want to log in using email and password so that I can securely access my account on any supported device. | 2
23 | Log out of the app | As a Player, I want to log out of the app so that I can securely end my session when I’m done using GolfR. | 1
24 | FaceID login | As a Player, I want to log in using FaceID so that I can access my account faster without repeatedly entering my password. | 1
25 | Navigation bar – switch between app features | As a Player, I want a navigation bar so that I can move between key app features quickly and consistently. | 3